## Risk Register
PayFlow Ltd — Information Security Risk Register
Prepared by: Bhuvana Kodathi Srinivas ¦ Version: 1.0 ¦ Date: June 2026 ¦ Framework: ISO 27001:2022 (Clause 6.1.2 — Risk Assessment)
Risk ID | Category | Risk Description | Threat Source | Likelihood (1-5) | Impact (1-5) | Risk Score (L x I) | Risk Level | Current Controls | Risk Owner | Remediation Action | Target Date
R-001 | Cybersecurity | Ransomware attack encrypting payment processing systems | External threat actor | 5 | 5 | 25 | Critical | Insufficient endpoint protection and backup testing | IT Department | Deploy EDR solution; test backup restore monthly; implement network segmentation | Q1 2026
R-002 | Cybersecurity | Phishing attack leading to credential compromise | External threat actor / social engineering | 5 | 4 | 20 | Critical | No email filtering or security awareness training in place | IT Department | Deploy email filtering; launch phishing simulation programme; enforce MFA on all accounts | Q1 2026
R-003 | Cybersecurity | SQL injection attack on payment processing API | External threat actor / automated scanning | 4 | 5 | 20 | Critical | No SAST or penetration testing conducted to date | Engineering Lead | Conduct annual penetration test; implement SAST in CI/CD pipeline; enforce OWASP Top 10 compliance | Q1 2026
R-004 | Cybersecurity | Unauthorised access to customer payment data via stolen credentials | External or insider threat | 4 | 5 | 20 | Critical | MFA not enforced on all systems; access reviews not conducted quarterly | IT Department | Enforce MFA on all systems; conduct quarterly access reviews; implement RBAC | Q1 2026
R-005 | Cybersecurity | DDoS attack causing platform unavailability | External threat actor | 3 | 4 | 12 | High | No DDoS mitigation service in place; single-region AWS deployment | IT Department | Implement AWS Shield Standard; configure auto-scaling; deploy to multiple AWS availability zones | Q2 2026
R-006 | Operational | System outage due to single point of failure in AWS infrastructure | Infrastructure failure | 3 | 5 | 15 | Critical | No multi-region deployment; RTO and RPO not formally defined | IT Department | Deploy to multiple AWS availability zones; define and test RTO (4hrs) and RPO (24hrs) | Q1 2026
R-007 | Operational | Data loss due to backup failure | Technical failure | 3 | 5 | 15 | Critical | Backups not tested regularly; no off-site backup storage | IT Department | Implement automated daily backups to separate AWS region; test restore monthly | Q1 2026
R-008 | Operational | Unauthorised system change causing platform instability | Internal human error | 3 | 4 | 12 | High | No formal change management process in place | IT Department | Implement formal change management procedure with approval sign-off and rollback plans | Q2 2026
R-009 | Operational | Payment processing errors due to software defect in production | Development error | 3 | 4 | 12 | High | No separation between development and production environments | Engineering Lead | Enforce strict environment separation; implement pre-production testing gate before all deployments | Q1 2026
R-010 | Compliance & Regulatory | GDPR enforcement action due to inadequate data protection practices | Regulatory / Data Protection Commission | 4 | 5 | 20 | Critical | No formal GDPR compliance programme; DPO not yet appointed | Legal / DPO | Appoint a Data Protection Officer; conduct GDPR gap analysis; implement data protection policies | Q1 2026
R-011 | Compliance & Regulatory | PCI-DSS non-compliance leading to loss of card processing rights | Regulatory / Payment card schemes | 4 | 5 | 20 | Critical | PCI-DSS assessment not yet conducted; cardholder data environment not formally scoped | IT Department / Legal | Engage a Qualified Security Assessor (QSA); scope cardholder data environment; remediate findings | Q1 2026
R-012 | Compliance & Regulatory | PSD2 non-compliance — failure to implement Strong Customer Authentication (SCA) | Regulatory / Central Bank of Ireland | 3 | 5 | 15 | Critical | SCA not fully implemented across all payment flows | Engineering Lead | Implement SCA across all payment flows; engage legal counsel to verify PSD2 compliance | Q2 2026
R-013 | Compliance & Regulatory | Failure to notify the Data Protection Commission within 72 hours of a data breach | Regulatory / GDPR Article 33 | 3 | 4 | 12 | High | No incident response plan or breach notification procedure in place | Legal / ISO Officer | Develop and test an Incident Response Plan with a documented 72-hour breach notification procedure | Q1 2026
R-014 | Third-Party / Vendor | Third-party payment processor suffers a data breach exposing PayFlow customer data | Vendor security failure | 4 | 5 | 20 | Critical | No vendor security assessments conducted; no security clauses in contracts | Legal / ISO Officer | Conduct vendor risk assessments; include security clauses and breach notification requirements in all contracts | Q1 2026
R-015 | Third-Party / Vendor | AWS service outage causing platform unavailability | Cloud provider failure | 3 | 5 | 15 | Critical | No multi-region failover; over-reliance on single AWS region | IT Department | Configure multi-region AWS deployment; implement automated failover; review AWS SLA | Q2 2026
R-016 | Third-Party / Vendor | Third-party software library vulnerability exploited in PayFlow application | Supply chain attack | 4 | 4 | 16 | Critical | No software composition analysis (SCA) conducted on third-party libraries | Engineering Lead | Implement SCA tooling in CI/CD pipeline; review and update all third-party dependencies monthly | Q1 2026
R-017 | Third-Party / Vendor | Subcontractor accesses PayFlow customer data without authorisation | Vendor / insider threat | 3 | 4 | 12 | High | No restrictions on subcontractor data access; no NDAs in place | Legal | Implement subcontractor access controls; require NDAs before data access; conduct annual vendor reviews | Q2 2026
R-018 | Physical & Environmental | Theft of employee laptop containing sensitive customer data | Physical theft | 3 | 4 | 12 | High | Device encryption not enforced on all laptops; no MDM in place | IT Department | Enforce full disk encryption on all devices; deploy MDM with remote wipe capability | Q1 2026
R-019 | Physical & Environmental | Office flood or fire causing loss of on-site equipment and data | Environmental hazard | 2 | 4 | 8 | High | No business continuity plan; no off-site data storage | IT Department / Facilities | Develop Business Continuity Plan; ensure all data stored in AWS with daily off-site backups | Q2 2026
R-020 | Physical & Environmental | Unauthorised physical access to PayFlow office gaining access to systems | Physical security breach | 2 | 4 | 8 | High | No key card access control; visitor log not maintained | Facilities Manager | Implement key card access control; enforce visitor sign-in policy; install CCTV at entry points | Q2 2026
R-021 | Financial | Payment fraud resulting in significant financial loss to PayFlow or its merchants | Fraudulent transactions / external threat | 4 | 5 | 20 | Critical | No fraud detection system in place; no transaction monitoring | IT Department / Finance | Implement real-time transaction monitoring and fraud detection; define chargeback management procedures | Q1 2026
R-022 | Financial | Insufficient cyber insurance coverage leaving PayFlow exposed to breach costs | Financial planning gap | 3 | 4 | 12 | High | No cyber insurance policy in place | Finance Director | Obtain cyber insurance policy covering data breach, ransomware, and business interruption costs | Q1 2026
R-023 | Financial | Security budget constraints limiting ability to implement critical controls | Internal financial risk | 3 | 4 | 12 | High | Security budget not formally allocated; controls deprioritised against product development | CEO / Finance Director | Formally allocate annual information security budget; present risk-based business case to board | Q1 2026
R-024 | People / Human | Key person dependency — critical security knowledge held by single staff member | Human / organisational risk | 4 | 4 | 16 | Critical | No documented security procedures; knowledge not transferred across team | ISO Officer / HR | Document all security procedures; implement cross-training programme; maintain succession plan | Q2 2026
R-025 | People / Human | Insider threat — disgruntled employee deliberately exfiltrates customer payment data | Malicious insider | 3 | 5 | 15 | Critical | No DLP controls; no user behaviour monitoring; access reviews not conducted | IT Department / HR | Implement DLP tooling; conduct quarterly access reviews; monitor privileged user activity | Q1 2026
R-026 | People / Human | Human error leading to accidental disclosure of customer data | Unintentional insider threat | 4 | 4 | 16 | Critical | No data handling training; no data classification policy implemented | ISO Officer | Implement data classification policy; deliver mandatory data handling training to all staff | Q1 2026

## Heat Map
PayFlow Ltd — Risk Heat Map (Likelihood vs Impact)
Risk Level Legend | LIKELIHOOD vs IMPACT HEAT MAP
Critical (15-25) |  | Impact 1 Negligible | Impact 2 Minor | Impact 3 Moderate | Impact 4 Major | Impact 5 Catastrophic
High (8-14) | Likelihood 5 Almost Certain | 5 | 10 | 15 | 20 R-002 | 25 R-001
Medium (4-7) | Likelihood 4 Likely | 4 | 8 | 12 | 16 R-016, R-024, R-026 | 20 R-003, R-004, R-010, R-011, R-014, R-021
Low (1-3) | Likelihood 3 Possible | 3 | 6 | 9 | 12 R-005, R-008, R-009, R-013, R-017, R-018, R-022, R-023 | 15 R-006, R-007, R-012, R-015, R-025
| Likelihood 2 Unlikely | 2 | 4 | 6 | 8 R-019, R-020 | 10
| Likelihood 1 Rare | 1 | 2 | 3 | 4 | 5

## Summary
PayFlow Ltd — Risk Summary Dashboard
Risk Level Summary
Risk Level | Count
Critical | 16
High | 10
Medium | 0
Low | 0
Total Risks | 26
Risks by Category
Category | Count
Cybersecurity | 5
Operational | 4
Compliance & Regulatory | 4
Third-Party / Vendor | 4
Physical & Environmental | 3
Financial | 3
People / Human | 3